## Slide 1: FCalPulse Local Mtg
J.Rutherfoord
20 May 2021
v2

## Slide 2: Outline
Welcome
Latest news
Beamline planning meeting
Rob Walker
  Updates
Dan Tompkins
  Status of the register

## Slide 3: SPS North Area H2/H4 Users Mtg
H2/H4 Users Meeting this morning
  Show drawings
Deployment in H2 beam line, zone PPE 172
  No installation until start date of Aug 4
  Need staging area ahead of occupancy
  Barracks HNA 383 (on mezzanine?)
  H2 beam height off the floor: 2460 mm

## Slide 6: Our assigned H2 beam area

## Slide 8: Possible schedule
2 July Ship equipment to CERN
18 July Team arrives at CERN
19 July Get CERN ID and rad badges
20 July – 3 Aug
  Stage our apparatus (Where?)
  Arrange safety inspections
  Organize gas and cryo deliveries
  Set up trigger electronics
  Take required training

## Slide 9: Possible schedule – Con’t
4 Aug Install our experiment and oversee infrastructure deployment
  When beam returns at the end of the day
    Start cryostat cool-down?
    Time-in the trigger
    Use BPCs to locate and tune beam

## Slide 10: Possible Schedule – Con’t
5 Aug
  Beam tuning
  DAQ commissioning
  Trouble shooting all systems
6 – 10 Aug Normal (?) data taking
  Cycle thru O2 contamination
    Cycle thru HV settings and polarity to the rod/tube electrode
      Cycle between up/down assemblies

## Slide 11: Critical Milestones (With dates)
Receive Sr-90 source from IPPE ?
Prepare system DAQ test – Start 17 May
Full system DAQ test – Start 14 Jun
Full system cryo test – Start 21 Jun
  Determine Sr-90 activity
  How to beat down the electronics noise
Ship apparatus to CERN – 7 Jul
Team arrives at CERN – 21 Jul
Beam starts – 4 Aug