## Slide 1: FCalPulse Local Mtg
J.Rutherfoord
10 Jun 2021
v2

## Slide 2: Outline
Latest news
Organization on the Platform in the zone
Rob Walker – Updates
Erich Varnes – Latest status of the DAQ
Graham Woolley – Preliminary noise measurement

## Slide 3: DAQ Run States
All are either true or false
  Run in progress
  Spill in progress
  Pause in progress
  Narrow beam
  Beam Halo veto
  Sr90 in beam

Allow triggers

## Slide 4: FCalPulse in our H2 zone
9 m

## Slide 6: Tentative schedule
2 July Ship equipment to CERN
18 July Team arrives at CERN
19 July Get CERN ID and rad badges
20 July – 3 Aug
  Stage our apparatus in PPE 182
  Arrange safety inspections
  Organize gas and cryo deliveries
  Set up trigger electronics
  Take required training

## Slide 7: Tentative schedule – Con’t
4 Aug Supervise infrastructure deployment and install our experiment
  When beam returns at the end of the day
    Start cryostat cool-down?
    Time-in the trigger
    Use BPCs to locate and tune beam
4 Aug (evening) to 5 Aug Tune beam
5 Aug – 11 Aug (morning) Take data

## Slide 8: Tentative Schedule – Con’t
5 Aug
  Beam tuning
  DAQ commissioning
  Trouble-shooting all systems
6 – 10 Aug Normal (?) data taking
  Cycle thru O2 contamination
    Cycle thru HV settings and polarity to the rod/tube electrode
      Cycle between up/down assemblies

## Slide 9: Critical Milestones (With dates)
Receive Sr-90 source from IPPE ?
Prepare system DAQ test – Start 17 May
Full system DAQ test – Start 14 Jun
Full system cryo test – Start 21 Jun
  Determine Sr-90 activity
  How to beat down the electronics noise
Ship apparatus to CERN – 7 Jul
Team arrives at CERN – 21 Jul
Beam starts – 4 Aug