## Slide 1: FCalPulse Local Mtg
J.Rutherfoord
24 Jun 2021
v1

## Slide 2: Outline
Latest news
Rob Walker – Shipping plans and cryo diagnostics
Sasha Savin – Update on the trigger scintillators
Graham Woolley – Diagnostics

## Slide 3: We need Swiss visas
This means we must all travel to San Francisco to register and leave our passports
You must email the Swiss visa office to make an appointment. You will need to attach an invitation from CERN
You must request an invitation from the ATLAS Secretariat (I’ve done that already so now we must follow up.)

## Slide 4: Tentative schedule
2 July Ship equipment to CERN
18 July Team arrives at CERN
19 July Get CERN ID and rad badges
20 July – 3 Aug
  Stage our apparatus in PPE 182
  Arrange safety inspections
  Organize gas and cryo deliveries
  Set up trigger electronics
  Take required training

## Slide 5: Tentative schedule – Con’t
4 Aug Supervise infrastructure deployment and install our experiment
  When beam returns at the end of the day
    Start cryostat cool-down?
    Time-in the trigger
    Use BPCs to locate and tune beam
4 Aug (evening) to 5 Aug Tune beam
5 Aug – 11 Aug (morning) Take data

## Slide 6: Tentative Schedule – Con’t
5 Aug
  Beam tuning
  DAQ commissioning
  Trouble-shooting all systems
6 – 10 Aug Normal (?) data taking
  Cycle thru O2 contamination
    Cycle thru HV settings and polarity to the rod/tube electrode
      Cycle between up/down assemblies
  Study x-talk between tube segments

## Slide 7: Critical Milestones (With dates)
Receive Sr-90 source from IPPE ?
Prepare system DAQ test – Start 17 May
Full system DAQ test – Start 14 Jun
Full system cryo test – Start 21 Jun
  Determine Sr-90 activity
  How to beat down the electronics noise
Ship apparatus to CERN – 7 Jul
Team arrives at CERN – 21 Jul
Beam starts – 4 Aug