## Slide 1: Schedule and Issues for the Mini-1 and MMFE-8
Kenneth Johns
University of Arizona

## Slide 2: Mini-1 Schedule
Task | Duration
Design | 90 days (from 12/1/13)
Design review and order parts | 3/1/14
Layout | 30 days (done 3/31/14)
PCB fabrication | 10 days
PCB assembly – 20 pcs | 20 days (done 4/30/14)
testing | 
Mini-1 is intended for bench tests of the VMM2

## Slide 3: MMFE-8 Schedule
Task | Duration
Design | 105 days (from 12/1/14)
Design review and order parts | 3/1/14
Layout | 45 days (done 4/30/14)
PCB initial fabrication + | 
PCB initial assembly | 30 days
PCB initial testing | 15 days (done 6/14/14)
PCB fabrication + | 
PCB assembly | 35 days (done 7/19/14)
PCB testing | 
PCB for distribution | 8/15/14?

## Slide 4: MMFE Demonstrator Costs
 | Production | Small Quantity
Parts | $568000 | $1101046
Fabrication | $165000 | $415800
Assembly | $343000 | $864360
NRE | $1300 | $3276
Total | $1077300 | $2384482
1 MMFE board | $229 | $506
1 board incl FPGA |  | $821
Costs are in USD and include indirect costs of 26%
Costs do NOT include VMM IC costs or SCA IC costs

## Slide 5: Other Boards Needed
S6-FMC board
  Design complete but needs layout and production
68p Mini-SAS (from Mini-1) to 80p Molex (for BNL) adapter board
  Design not started, but have an earlier 80p Molex adapter design (to 60p TE connector) to work from
Test fixture (pulser board) for MMFE-8 (not thought about, not started, not scheduled)

## Slide 6: Outstanding Issues
Mini-1
  Can proceed in early January as Dan is available
  Needs VMM2 packaging and pinout
MMFE-8
  In early stages of design
  Needs VMM2 packaging and pinout
  Multidrop capability not settled
  Power scheme(s) must be discussed and specified
  Power for and configuration of FPGA must be specified (from Lorne)

## Slide 7: Outstanding Issues
MMFE-8
  Clock distribution must be specified
  GbE connector must be specified
  Input protection choice must be made
  SRS I/O must be specified
  Cooling is not addressed
  RF cage requirement is not settled
  Integration with MM chamber not specified or even thought about

## Slide 8: Outstanding Issues
Software and firmware
  A local DAQ scheme must be baselined (IPBUS, MicroBlaze, something else, …)
  Host PC configuration and control software (Python, Qt, …)
  Large list of firmware tasks
    Multi-chip configuration
    UDP GbE output needs to be implemented
    Algorithm and output for L1DDC
    Run modes – bench, test beam, ATLAS
    …

## Slide 9: Conclusions
I have confidence we can produce the Mini-1 on a timescale compatible with VMM2
The MMFE-8 demonstrator card will likely not be available until August, 2014
A significant software and firmware effort must also accompany this card